## BACKLOG
AGILE PRODUCT BACKLOG FOR GROUP G CAPSTONE PROJECT
TICKET ID | TICKET NAME | SPRINT # | ASSIGNED TO | START | FINISH | DESCRIPTION | SPRINT READY | PRIORITY | STATUS | SPRINT MASTER
|  | SPRINT 1 | [7 empty] | Kevin An Thai Nguyen
TICKET1 SPRINT1 | Fall25_S1_Ticket 1 | Sprint 1 | Camden Laskie | 2025-09-01 | 2025-09-26 | Collaborate with Group G to create website redesign template in figma | No | High | In Progress
TICKET2 SPRINT1 | Fall25_S1_Ticket 2 | Sprint 1 | Camden Laskie | 2025-09-01 | 2025-09-26 | Meet with users of products to determine needs and create outline for project | No | High | In Progress |  | This section is for the drop-down list
TICKET3 SPRINT1 | Fall25_S1_Ticket 3 | Sprint 1 | Kevin An Thai Nguyen | 2025-09-01 | 2025-09-26 | Create the absolute minimum non AI approach to show as working prototype | No | High | In Progress |  | Yes | High | Complete
TICKET4 SPRINT1 | Fall25_S1_Ticket 4 | Sprint 1 | Natalie Roman | 2025-09-01 | 2025-09-26 | Create ai approach to grading. As basic as possible at first to show in demo for Norman PD | No | High | In Progress |  | No | Medium | In Progress
TICKET5 SPRINT1 | Fall25_S1_Ticket 5 | Sprint 1 | Jaiden Sizemore | 2025-09-01 | 2025-09-26 | Parse given transcripts to help create non ai grading algorithm | No | High | In Progress
|  | Sprint 2 | [7 empty] | Jaiden Sizemore |  | Low | Not Started
|  | Sprint 3 | [7 empty] | Natalie Roman
Sprint 4
Sprint 5
Sprint 6
Sprint 7