## BACKLOG
AGILE PRODUCT BACKLOG FOR GROUP G CAPSTONE PROJECT
TICKET ID | TICKET NAME | SPRINT # | ASSIGNED TO | START | FINISH | DESCRIPTION | SPRINT READY | PRIORITY | STATUS | SPRINT MASTER | FEATURES | USER STORY
|  | SPRINT 1 | [7 empty] | Kevin An Thai Nguyen
TICKET1 SPRINT1 | Fall25_S1_Ticket 1 | Sprint 1 | Camden Laskie | 2025-09-01 | 2025-09-26 | Collaborate with Group G to create website redesign template in figma | Yes | High | Completed |  | Accessible, clean, easy-to-use interface for grading dashboard | As a dispatcher manager at NPD I would like a clean, easy, modern and user friendly interface
TICKET2 SPRINT1 | Fall25_S1_Ticket 2 | Sprint 1 | Camden Laskie | 2025-09-01 | 2025-09-26 | Meet with users of products to determine needs and create outline for project | Yes | High | Completed |  | User research with their feedback in what they require from the project | As a dispatcher manager at NPD, I have specific requests in grading, it is very strict on grading therefore these need to be listed. | This section is for the drop-down list
TICKET3 SPRINT1 | Fall25_S1_Ticket 3 | Sprint 1 | Kevin An Thai Nguyen | 2025-09-01 | 2025-09-26 | Create the absolute minimum non AI approach to show as working prototype | Yes | High | Completed |  | Non-AI Grading prototype | As developers, we want the user to have a basic non-ai demo so that our users can visualize and interact with our system | Yes | High | Complete
TICKET4 SPRINT1 | Fall25_S1_Ticket 4 | Sprint 1 | Natalie Roman | 2025-09-01 | 2025-09-26 | Create ai approach to grading. As basic as possible at first to show in demo for Norman PD | Yes | High | Completed |  | Basic AI Grading Demo | As developers, we feel a model would help tremendously for the efficiency and accuracy of this program and we would like to implement that. | No | Medium | In Progress
TICKET5 SPRINT1 | Fall25_S1_Ticket 5 | Sprint 1 | Jaiden Sizemore | 2025-09-01 | 2025-09-26 | Parse given transcripts to help create non ai grading algorithm | Yes | High | Completed |  | Transcript parser | As a dispatcher, it is good to have our conversations saved on file for grading and review. As developers, to have this json formatted for us is more structured and better to implement our grading systems.
|  | Sprint 2 | [7 empty] | Jaiden Sizemore |  |  |  | Low | Not Started
TICKET1 SPRINT2 | Fall25_S2_Ticket 1 | Sprint 2 | Camden Laskie | 2025-09-27 | 2025-10-22 | Create the rest of frontend/code or figma | No | High | In Progress |  | Frontend Expanded | As a dispatcher,, I want an easy to use interface where I can review my grading protocols and calls.
TICKET2 SPRINT2 | Fall25_S2_Ticket 2 | Sprint 2 | Kevin: Add grading for chest pain related questions. Jaiden: Add grading for animal attack related questions. | 2025-09-27 | 2025-10-22 | Scaling the non ai demo | No | High | In Progress |  | Expanded Grading system | As a police dispatcher in training, I want a grading system that includes certain nature codes
TICKET3 SPRINT2 | Fall25_S2_Ticket 3 | Sprint 2 | Natalie Roman | 2025-09-27 | 2025-10-22 | Create a program that takes protocols given from NPD to create our own csv, | Yes | High | Completed |  | Protocols to CSV tool | As the NPD IT team, it is important that we have protocols saved in a structured fashion not only for tools like this but to make grading more efficient and accurate.
TICKET4 SPRINT2 | Fall25_S2_Ticket 4 | Sprint 2 | Natalie Roman | 2025-09-27 | 2025-10-22 | keep researching ai approach maybe for sprint 3 if non ai is working | No | Low priority | In progress |  | AI research | As NPD IT crew, we want an implementation on how to incorporate AI in the upcoming semestes.
|  | Sprint 3 | [7 empty] | Natalie Roman
TICKET1 SPRINT3 | Fall25_S3_Ticket 1 | Sprint 3 | Camden Laskie | 2025-10-23 | / | Finish frontend, diff grading pages on figma and vs | No | High | Not completed
TICKET2 SPRINT3 | Fall25_S3_Ticket 2 | Sprint 3 | Kevin An Thai Nguyen | 2025-10-23 | / | Help refine nonai grader and ai grader to the parse protocols csv and given json files | No | High | Not completed
TICKET3 SPRINT3 | Fall25_S3_Ticket 3 | Sprint 3 | Jaiden Sizemore | 2025-10-23 | / | Help Kevin refine our grading templates | No | High | Not completed
TICKET4 SPRINT3 | Fall25_S3_Ticket 4 | Sprint 3 | Natalie Roman | 2025-10-23 | / | Review parsed manually inputted protocols and come up with list of constraints/rules for grader | No | High | Not completed
TICKET5 SPRINT3 | Fall25_S3_Ticket 5 | Sprint 3 | Natalie Roman | 2025-10-23 | / | Help with frontend figma designs | No | High | Not completed
TICKET6 SPRINT3 | Fall25_S3_Ticket 6 | Sprint 3 | Everyone | 2025-10-23 |  | Help connect our frontend and backend to Group B's project and prepare for final demo.. | No | Mid priority | Not completed
Sprint 4
Sprint 5
Sprint 6
Sprint 7